## Slide 1: HOM – Project Management Module

## Slide 2: Introduction
The time management function of HOM allows the user to analyze the process required to complete a time dependent project such as
  New product introduction campaign
  A consulting or accounting engagement
  Software development

## Slide 3: Introduction(2)
The key questions a manager might want to answer are
  What is the shortest time it will take me to complete the project?
  Can I save time if I invest financial resources, and where should I invest financial resources, and when should this be done?
  If I’m not certain of exactly how long a task will take, can I determine the likelihood of the project taking a fixed amount of time?

## Slide 4: Introduction(3)
The key to being able to answer the above questions depends on the user’s ability to initially specify
  The tasks involved in the project
  Duration of each task
  The order in which the tasks must be completed ( precedence relationships)
Details on entering data are provided below

## Slide 5: Working in the HOM application

## Slide 6: Introduction to HOM - Project Management module
To run the HOM – Project Management module, select HOM module from the Add-Ins option and, select Project Management Module.
This will take you to a screen which allows you to determine which data you wish to analyze. More information is given on this in the next few steps.

## Slide 7: The HOM Project Management Schema

## Slide 8: Parameters Dialog Box
HOM module allows the user to specify the settings in the Parameters dialog box. A sample parameters dialog box is given below.

## Slide 9: Parameters Dialog Box
Select Data
The user can either load data from reloadable examples or insert their own data using the method described below
Reload Datasets:
To reload saved reports please follow the steps below:
Open ‘HOM Project’ from the HOM menu.
Click the reload button which will ask the user to select Report file (.csv) which the user wishes to open.
Select the file and click ‘Open’, this will reload all the parameters for computing.

## Slide 10: Project Management - Steps
Step I: Choose technique
    Specify which type of problem is being solved select one of radio buttons from CPM data or Crashing data or PERT data
Step II: Select Data (Parameters Box)
    Input the starting and ending row of the data (between row 4 to 205)
              or
  Reload Datasets
    Open ‘HOM Project Management Module’ from HOM menu
    Click the reload button which ill ask the user to select Report file(.csv) which the user wishes to open
    Select the file and click ‘Open’ this will reload all the parameters from computing
    Click ‘Compute’ to reload the result sheets

## Slide 11: Project Management - Steps
Step III: Draw Activity Network (Parameters Box)
    Check the Draw Activity Network button to see a drawing of the network of activities. This can be done under both CPM and PERT.
    Step IV: Run Model (How to Manage Projects)
    To run the model you have to click on the specified compute button. This will open up one or more worksheets with the data analysis and results

## Slide 12: Project Management - Steps
Step V: Analyze and Save Results
    Analyze Results
      CPM
        The CPM window contains the GANTT chart (both early and late start schedule can be plotted)
        The next part of the result window shows critical path calculations
        The next output item is the project completion time, and finally a list of those activities on the critical path

## Slide 13: Project Management - Steps
Step VI: Analyze Results
    Analyze Results
      PERT
        Two possible results based on simulation is selected or not
        Without Simulation the result window shows Gantt Chart followed by PERT calculation
        The total project expected completion time is given next followed by the standard deviation of the expected time on the critical path

## Slide 14: Project Management - Steps
Step VII: Save Reports button
    Single Save
      To save report, user can click Save button followed by specifying the name of the report to be saved
    Multiple Save
      For multiple save, user can press ‘Ctrl + S’ or ‘Save ’ button from Menu followed by selecting the sheets which are not shaved.

## Slide 15: Loading an example
To obtain the dialog box, select HOM module from the Add-Ins option on the tool bar.
  This will open the Dialog box which allows you to select which method to use. Sample parameters Dialog box is given below.
Press Reload button on the dialog box to load an example. Example 1 can be found in the data file
Project_CPM_time.csv in the EXAMPLES directory.

## Slide 16: Loading an example
Following is the screenshot of the same

## Slide 17: Data Set Loaded
Reload | CPM data | Crashing Data |  | PERT Data |  |  |  |  | 
Activity Code | Normal Duration | Minimum Duration | Cost per Unit | Optimistic Time | Likely Time | Pessimistic Time | Pred. 1 | Pred. 2 | Pred. 3
move | 2 | 1 | 1000 | 2 | 2 | 2 |  |  | 
rbo | 4 | 3 | 6000 | 4 | 4 | 4 |  |  | 
frame1 | 3 | 2 | 5000 | 3 | 3 | 3 | rbo |  | 
wire1 | 6 | 4 | 5000 | 6 | 6 | 6 | frame1 |  | 
instal | 1 | 0.6 | 5000 | 0.4 | 0.6 | 0.8 | wire1 | move | 
ckt-a | 2 | 1 | 7500 | 2 | 2 | 2 | instal |  | 
conn | 1 | 0.7 | 6667 | 1 | 1 | 1 | ckt-a |  | 
ckt-b | 2 | 1 | 7500 | 2 | 2 | 2 | conn |  | 
walk1 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | ckt-b |  | 
touch1 | 1 | 0.7 | 5000 | 0.5 | 0.7 | 1 | walk1 |  | 
online | 0 | 0 | 0 | 0 | 0 | 0 | touch1 | touch3 | 
layout | 4 | 3 | 6000 | 1.5 | 3 | 4 |  |  | 
frame3 | 4 | 2.5 | 4667 | 1.5 | 2.5 | 4 | layout |  | 
roof | 3 | 2 | 6000 | 1 | 2 | 3 | frame3 |  | 
ext | 2 | 1 | 5000 | 2 | 2 | 2 | frame3 |  | 
plumb | 5 | 3 | 4000 | 5 | 5 | 5 | roof | ext | 
wire3 | 6 | 4 | 5000 | 2 | 4 | 6 | roof | ext | 
hvac | 4 | 3 | 3000 | 4 | 4 | 4 | roof | ext | 
insul | 2 | 1.5 | 8000 | 2 | 2 | 2 | plumb | wire3 | hvac
int | 2 | 1.5 | 6000 | 1 | 1.5 | 2 | insul |  | 
paint | 1 | 0.7 | 10000 | 1 | 1 | 1 | int |  | 
fixt | 1 | 0.7 | 6667 | 1 | 1 | 1 | paint |  | 
carpet | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | fixt |  | 
walk3 | 0.5 | 0.5 | 0 | 0.5 | 0.5 | 0.5 | carpet |  | 
touch3 | 1 | 0.7 | 5000 | 0.5 | 0.7 | 1 | walk3 |  | 
Home construction project!
CPM Selected
Each task can have upto 10 predecessors
Eg: Roof takes 3 units of time, predecessor is frame3
Can have up to 199 tasks
Must be entered in contiguous rows

## Slide 18: General Instruction on entering data
Fill in Activity names under the ACTIVITIES column. Names can be numbers, letters or short abbreviations. A more complete definition can be given for each activity, if desired, by moving the cursor to the extreme right of the spreadsheet to the optional activity DESCRIPTION column. Up to 199 activities can be specified .
Enter up to ten immediate predecessors for each task. If a task has only one immediate predecessor, enter it in column PRED 1. If it has two, use columns PRED 1 and PRED 2, and so on. The name used to identify the predecessor must be identical to its short activity name. A task without predecessors (i.e., starting tasks) will have no predecessors listed in its appropriate row.
If you plan to use CPM analysis, select CPM DATA and fill in the duration of each activity in the row corresponding to the activity under the column NORMAL DURATION. If you plan to use Crashing select CRASHING DATA. Then fill in the minimum duration that the activity can be crashed to under the appropriate column. If the minimum duration differs from the normal duration fill in the cost of crashing by one unit of time under the column COST PER UNIT.
If you plan to use PERT analysis, select PERT DATA. Fill in the Optimistic, Likely and Pessimistic times under the appropriate columns.
NOTE: Be sure to select the correct radio button(CPM data or Crashing data or PERT data) so that HOM will allow you to input the data you need.
Warning! Any data in sheet other than HOM sheet will be automatically deleted on exit. Output can be saved using the Save option. See Step VII

## Slide 19: Dialog Box Choices
CPM selected
Start Row
End Row
Data must be in contiguous row
If draw network selected will represent data as a network

## Slide 20: Output for Example (on pressing compute)
Gantt chart shows the earliest each task can be started and completed.
Table gives Early as well as late start (latest task can start without delaying the project.
Slack shows how much delay can be tolerated in the task w/o affecting project completion

## Slide 21: Output for Example
List of activities on critical path
Tasks that are critical have zero slack.
The longest path is called the critical path.

## Slide 22: Early vs Late Start Gantt Chart
Under graph options choose to visualize both schedules

## Slide 23: Drawing the project network
HOM can draw the network given the project data.

## Slide 24: CPM Crash
Minimum Duration: This is the minimum duration to which the activity can be crashed.
Cost/Time: The cost of reducing the duration of an activity (crashing) by a unit of time.
Activity Duration: This is the normal duration of the activity

## Slide 25: CPM and Crashing
Crashing the duration (reducing the duration) of an
activity increases the activity cost but may reduce the duration of the project. The latter has several project level benefits, such as:
Direct benefits
Indirect benefits
The objective is to trade-off these overall benefits against the cost of crashing activities

## Slide 26: Example of crashing
Overtime
Mechanization of work (crane or forklift)
Extra resources (labor, machines)
Faster logistics (air vs truck)
Not to be confused by parallelization or activity reversal

## Slide 27: CPM Crash Setting
In the dialog box choose Enable Cost Crashing. The data entry part for cost data will change in color to indicate editing is enabled.
There are two options:
  Determine the entire cost-time trade-off curve. This will compute the cost-time trade off from the normal to the minimum possible duration.
  Determine the optimal cost of reducing the project duration to a given value. Here, the user enters a value. If that value is infeasible, the program returns a message stating so.
  Examine the cost time trade-off data entered. You will notice some activities can not be reduced in duration. In that case set minimum duration = normal duration and crash cost = 0.

## Slide 28: CPM Crash Dialog Box
  We know the project can be completed in 25 days. Try to reduce it to 22 days.

## Slide 29: CPM Crash Output
Layout, frame3, wire3, touch3 are crashed.
Now there are two critical paths!

## Slide 30: Technical aside
Linear Program: When the calculations start, the given data are first converted into a linear program. The conversion method is outlined in Eppen, Gould and Schmidt, (1993). Then the resulting LP is solved by a standard two-phase simplex method.
If the task durations need to be integral then the problem becomes an integer program. Other interesting restrictions, including resource restrictions can be modeled (not in this version!).
For example (not in this version).
  One can model constraints such as concrete mixing can start soon as foundation 1 or foundation 2 is complete.
  Either the crane and loader must be free or else the crane and two dumpers are necessary.
  In general, rule based constraint programming is possible.

## Slide 31: Introduction to PERT
A
B
C
D
E
F
G
H
There is considerable uncertainty in task durations!

## Slide 32
ACTIVITY DURATIONS
MIN LIKELY MAX MEAN S.D.
---------------------------------------------------------------------------------------------------
A-B 2 5 8 5.00 1
A-D 4 5 7 5.17 0.5
A-E 6 8 12 8.33 2.0
B-C 1 3 7 3.33 1.0
C-G 2 4 5 3.83 0.5
D-G 8 9 11 9.17 0.5
E-F 4 5 7 5.17 0.5
F-G 6 8 10 8.00 0.67
G-H 1 2 3 2.00 0.33
----------------------------------------------------------------------------------------------------
MEAN = (MIN + 4*LIKELY + MAX)/6 due to beta distribution assumption.
STANDARD DEVIATION (S.D.) = (MAX - MIN)/6
Why 3 time
estimates?
How estimated?
Other options?
Introduction to PERT
PERT….

## Slide 33: Why three time durations?
Managers are able to estimate pessimistic, likely and optimistic times rather than mean and standard deviation.
Likely corresponds to the mode of the distribution.
Exact distribution can be used if available (not in this version).
The three time estimates are converted to the mean and standard deviation of the task duration
MEAN = (MIN + 4*LIKELY + MAX)/6 due to beta distribution assumption.
STANDARD DEVIATION (S.D.) = (MAX - MIN)/6
PERT….

## Slide 34: Draw the network and find critical path
PERT….
A
B
C
D
E
F
G
H
(5,1)
(3.33,1)
(9.17,0.5)
(8.33,1)
(5.17,0.5)
(5.17,0.5)
(8,0.67)
(2,0.33)
(3.83,0.5)

## Slide 35: Calculate the distribution of project completion time
PERT….

## Slide 36: Normal Approximation
PERT….

## Slide 37: Normal Approximation
Project completion time has Normal Distribution with mean 23.5 months and standard deviation 1.344.
Mean = 23.5
Standard Deviation = 1.344
Probability Completion Time <= 25 days
Pr{ Z <= (25 – 23.5)/1.344} = Pr{Z <= 1.12}
Project Duration, T
Probability
PERT….
What is the probability the project will take more than 26 days?

## Slide 38: Loading (PERT) example (same one)
To obtain the dialog box, select HOM module from the Add-Ins option on the tool bar.
  This will open the Dialog box which allows you to select which method to use. Sample parameters Dialog box is given below.
Press Reload button on the dialog box to load an example.
Project_PERT_Heuristic_New.csv in the EXAMPLES directory.
Look at the dialog box.

## Slide 39: PERT Data and Dialog Box

## Slide 40: PERT Output

## Slide 41: Simulation
Running a simulation gives more diagnostics!

## Slide 42: Simulation Output
Simulated distribution
Criticality Index: In what percentage of the simulations was the activity critical

## Slide 43: More examples
Likewise, user can work on other examples. Following are the datasets provided with this module.
    Project_CPM_time.csv
    Project_CPM_Costtime_tradeoff.csv
    Project_CPM_Costcrashing.csv
    Project_PERT_Heuristic.csv
    Project_PERT_Simulation.csv
Kindly refer to the manual and Tutorial for technical details and step-by-step procedure.

## Slide 44: Tasks
Practice problems
  Solve problems 1 (or 2)
  Solve problems 9 and 10
Solve the Campus Wedding Case (A)